## TestScenarios
Project Name | Pickaboo
Reference Document | FRS
Created By | Jannatul Ferdous Samia
Creation Date | 20-05-2026
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the URL in different browsers. | P0 | 1
TS_002 |  | Validate the "Register Account" functionality | P1 | 27
TS_003 |  | Validate the working of the "Add cart functionality" functionality. | P1 | 15
TS_004 |  | Validate the working save address | P1 | 7
TS_005 |  | Validate the working of " Search Bar" functionality. | P4 | 9
TS_006 |  | Validate the working of "OTP" functionality. | P1 | 1
TS_007 |  | Validate the working of "Forgotten Password" functionality. | P2 | 1
TS_008 |  | Validate the working of "Accessories" functionality. | P4 | 1
TS_009 |  | Validate the working of "Support" functionality. | P5 | 1
TS_010 |  | Validate the working of "Address" functionality. | P5 | 1
TS_011 |  | Validate the working of "About usl" functionality. | P5 | 1
TS_012 |  | Validate the working of "Download" functionality. | P5 | 1
TS_013 |  | Validate the working of "Social"functionality. | P5 | 1

## TestCase
Product Name | pikaboo | TC Start Date | 15/08/2025 | TC Execution Start Date | 14/10/2025 |  |  |  |  | Test Case
Module Name | Account | TC End Date | 17/08/2025 | TC Execution End Date | 15/11/2025 |  |  |  |  | PASSED | 102
Epic |  | Test Case Developer By | md . Tarekur | Browser (tested) | Yes |  |  |  |  | FAILED | 11
Developer Name (TL) |  | Test Case Reviewed By | Samia | Performance (tested) | Yes |  |  |  |  | NO RUN | 0
[10 empty] | BLOCKED | 0
Test Executed by | [9 empty] | TOTAL | 0
Serial | Module | Type of Testing | Features | Test Cases | Test Data | Exepected Result | Actual Result | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Account | Browser Compatibility | Browser | Verify that the URL run in different browsers | Brave, Chrome, Microsoft edge | Should be run in different browser | Found as per expectation. |  |  | Passed
Test Case for Registration Module
2 |  |  | Home Page | Verify that the logo of the Home Page | Logo | The logo should be clickable | Found as per expectation. |  |  | Passed
|  |  | Header Section | Vedrify that the tagline is visible or not | Tagline | The tagline should be display | Found as per expectation. |  |  | Passed
3 |  |  |  | Verify that the there is no grammar,spellig ,Punctuation or Language errors | N/A | Should not be any spelling or grammar errors | Found as per expectation. |  |  | Passed
4 |  |  | Search box | Verify that the click on search box | click on search box | The system should be click on search box | Found as per expectation. |  |  | Passed
5 |  |  |  | Verify that the Search with valid product name | Search on valid product | the product is searched that is valid or not | Found as per expectation. |  |  | Passed
6 |  |  |  | Verify that the placeholder is present in search box | Placeholder | The website should have placeholder in search box | Found as per expectation. |  |  | Passed
7 |  |  |  | Verify that the type of minimum character in search box | Type of minimum character | The display should display an error message to the required character | Found as per expectation. |  |  | Passed
8 |  |  |  | Verify that the type of maximum number in search box | Type of maximum character | The system should display an error message according to the required number | Found as per expectation. |  |  | Passed
9 |  |  | Register | Verify that the without verification phone number | Without verification phone number | The verification should not work and displayed registered properly without 11 digits phone number | Found as per expectation. |  |  | Passed
10 |  |  |  | Check that the phone number is 11 digits or not | Verify with proper 11 digits phone number | phone number should be 11 digits | Found as per expectation. |  |  | Passed
11 |  |  |  | Verify that the with verification phone number | Verification phone number | The verification not work and displayed registered properly with 11 digits phone number | Found as per expectation. |  |  | Passed
12 |  |  |  | Verify that the asterrisk sign in name field | Asterisk sign | The system should have a asterisk sign | Not Found as per expectation. |  |  | Failed
13 |  |  |  | Verify that the special character in name field | Special character : %, $, #, @, !, &,* | The system should not work and displayed with special sign | Found as per expectation |  |  | Passed
14 |  |  |  | Verify that the placeholder is present in name field | Placeholder | The system should have placeholder | Found as per expectation. |  |  | Passed
15 |  |  |  | Verify that the minimum type of character in name field | Minimum character - d | The system should not work and displayed the required quantity of minimum character | Not Found as per expectation. |  |  | Failed
16 |  |  |  | Verify that the maximum type of character in name field | Maximum character - mdsojfnsefgipesfjg vmkdffvpokfjkd vkmdpjrjonwmamv | The system should not work and displayed the required quantity of maximum character | Foumd as per expectation |  |  | Passed
17 |  |  |  | Verify that the submitted all field without name field | Without name field | The system should not work and displayed without proper first name | Foumd as per expectation |  |  | Passed
18 |  |  |  | Verify that the submitted all field without last name field | Without last name field | The system should not work and displayed without proper last name | Not found as per expectation |  |  | Failed
19 |  |  |  | Verify that the submitted all field without first name field | Without first name field | The system should not work and displayed without proper first name | Not found as per expectation |  |  | FAiled
20 |  |  |  | Verify that the submitted without required field are empty | Empty field | The system should not work and displayed | Found as per expectation |  |  | Passed
21 |  |  |  | Verify that the submitted all field without email field | Empty email field | The system should not work without email | Found as per expectation. |  |  | Passed
22 |  |  |  | Verify that the submitted wrong email | Wrong email jdhfh.com | Should not work | Found as per expectation. |  |  | Passed
23 |  |  |  | Verify that the submitted email without @ | wrong email hy3.com | should not work | Found as per expectation. |  |  | Passed
24 |  |  | Password | Verify that the submitted all field wihout all field | Empty password | The password system should not work | Found as per expectation. |  |  | Passed
25 |  |  |  | Verify that the password should be visible on tap of eye button and again became encrypted on double tab | click | should work | Not Found as per expectation. | file:///C:/Users/samia%20jannat/Downloads/Doc1.pdf |  | Failed
26 |  |  |  | Verify the the submitted weak password | Pop up error only number | The password system should not work | Found as per expectation. |  |  | Passed
27 |  |  |  | Verify that system shows a pop-up error meassage when the password contains only number | give password: 123456 | should display pop up message | Found as per expectation. |  |  | Passed
28 |  |  |  | Verify that the asterisk(*) sign in password field | Asterisk (*) sign in password field | The system should have the asterik sign | Found as per expectation |  |  | PAssed
29 |  |  |  | Verify logged-in user doesn’t log out by clicking the back button on the browsers tab. | check by clicking back button | should display | Found as per expectation. |  |  | Passed
30 |  |  |  | Verify that the submitted password section only special character | Special character : %, $, #, @, !, &,* | The password sysstem should not work | Found as per expectation. |  |  | Passed
31 |  |  | Cart Button | Verify that the cart button is work or not | Cart button | System should work and go to the next page | Found as per expectation. |  |  | Passed
32 |  |  |  | Verify that an undefine effect appears when the user hovers over the cart button | hovers over the cart button | The system should an underline or visual hover indicate that the cursor is hoverinf=g over it | Found as per expectation. |  |  | Passed
33 |  |  |  | Verify that the empty cart message is displayed when no items are added to the cart | empty cart message id displayed | the system should display an empty cart | Found as per expectation. |  |  | Passed
34 |  |  |  | Verify that the total cart is displayed after adding a product to the cart | The total cart is displayed after adding | The system should displayed total cart after adding product ot the cart | Found not as per expectation. |  |  | Failed
35 |  |  |  | Verify that the processed to check out box work or not | Proceed to checkout box is work or not | The system should have click to next option | Found as per expectation. |  |  | Passed
36 |  |  |  | Verify tha the total cart price is displaced after adding a product to the cart | Total cart price is displayed | The system should displayed total cart price | Found not as per expectation. |  |  | Failed
37 |  |  |  | Verify that the chatbox is work or not | Chat box work or not | Thee system must work when cllick the chat | Found not as per expectation. |  |  | Failed
38 |  |  |  | Verify that the add new address save successfully | edit and save new address | should save new address | Found as per expectation |  |  | Passed
39 |  |  |  | Verify that the all required option in add new adress field | Dhaka | Should be add new address | Found as per expectation |  |  | Passed
40 |  |  |  | Verify that the add new address save successfully | Add new address save | The system should have work properly | Found as per expectation |  |  | Passed
41 |  |  |  | Verify that the change address | Changaddress | The system should change address or editClick on search box | Found as per expectation |  |  | Passed
42 |  |  |  | Verify that the all required option in addnew field | All required option in add new address field | should have all required field | Found as per expectation |  |  | Passed
43 |  |  | Add new adress option | Verify that the auto is selected | auto area selected | The system should select auto area when give new addresses | Found as per expectation |  |  | Passed
44 |  |  | Search box | Verify that the account information is editable or not | Edit account information | It should edit all information | Found as per expectation |  |  | Passed
45 |  |  |  | Verify that the change email address | Change email address | It should be changed | Found as per expectation |  |  | Passed
46 |  |  |  | Verify that the placeholder is present in change email option | placeholder is present in change email option | The system should haave present in email field | Found as per expectation | s |  | Passed
47 |  |  |  | Verify that the save button is work | Save button is work | It should be wrok properly to save | Found as per expectation |  |  | Passed
48 |  |  |  | Verify that my order button is clickable or not | Order button | It should be clickable and go to next page | Found as per expectation |  |  | Passed
49 |  |  |  | Verify that the my order option is despalyed when no items are ordered | Empty my order option is displayed when no item are order | When no order to submitted, displayed to show | Found as per expectation |  |  | Passed
50 |  |  |  | Verify that the pickaboo club option is work or not | Pickaboo option buttonn work or not | When click pickaboo option it should takes to next page | Found as per expectation |  |  | Passed
51 |  |  |  | Verify that a chatbox is available in my order section | Chat box in my order section | A chat box is available in every section | Found as per expectation |  |  | Passed
52 |  |  |  | Verify in order section chat box has work or not | A chat box is work | It successfully work | Found as per expectation |  |  | Passed
53 |  |  |  | Verify that he empty my product review is displayed when no order to confirm | Empty my product review | When no order to submitted, displayed to show | Found as per expectation
54 |  |  |  | Verify that a chat box is available or not in my product review section | chat box is available in my product review section | As per as expected | Found as per expectation |  |  | Passed
55 |  |  |  | Verify that my product review chat box is work or not | A chat box is work or not in my product review | As per as expected | Found as per expectation |  |  | Passed
56 |  |  |  | Verify that the point summary option work or not under pickaboo club | My point summary | It should clickable and go to next page | Found as per expectation |  |  | Passed
57 |  |  |  | Verify that the every single option work or not under my account | Every single option work or not under my account | I should be work properly and displayed | Found as per expectation |  |  | Passed
58 |  |  | Navigation menu icon | Veirfy that the three dots navigation icon work or not | three dot navigation icon work or not | it should be work,clickable and sggestable | Found as per expectation |  |  | Passed
59 |  |  |  | Verify that the first navigation catagories air conditioner work or not | firsst navigation | It should be clickable and go to next page | Found as per expectation |  |  | Passed
60 |  |  |  | Verify that the first navigation air conditioner suggest all bands | Suggest all brand in first navigation | It should be suggests all brands | Found as per expectation |  |  | Passed
61 |  |  |  | Verify that the clickable all brands | clickable all brands | It should be clickable all brands and displayed | Found as per expectation |  |  | Passed
62 |  |  |  | Verify that the displayed proper details in one brands | proper details | It should be proper diplayed in details | Found as per expectation |  |  | Passed
63 |  |  |  | Verify that the total number of items for a brand is displayed | total item | It should be diaplayed properly , how many items can displayed | Found as per expectation |  |  | Passed
64 |  |  |  | Verify that the price range min or max is present or not | price range | It should be work and type minimum to range | Found as per expectation |  |  | Passed
65 |  |  |  | Verify that the price range is work or not | rice range | It should not be work for minimum and maximum to range | Found as per expectation |  |  | Passed
66 |  |  |  | Verify that the given maximum minimum price | Maximum minimum price/20000 | It should work and displayed if 20000 | Found as per expectation |  |  | Passed
67 |  |  |  | Verify that the given maximum to maximum price | Maximum price 20000000 | I should be work and displayed if 200000 | Found as per expectation |  |  | Passed
68 |  |  |  | Verify that no products available message is dsplayed when no products are found | What message is displayed when products are not available | When product are not available it show it’s not available now | Found as per expectation |  |  | Passed
69 |  |  |  | Verify that a chatbox is available in every brands option | Chat box is available or not in every brand function option | A chat box is mendatory in every brand | Found as per expectation |  |  | Passed
70 |  |  |  | Verify that the display size (inch) is working or not | Display size | It should be wrok properly and go to next page | Found as per expectation |  |  | Passed
71 |  |  |  | Verify that products are displayed based on the selected ram size | Displayed based on the selected ram size | The system should be displayed only the products bassed on the rsm based | Found as per expectation |  |  | Passed
72 |  |  |  | Verify that the user can select a express delivery checkbox | select a future checkbox | The system should be selcted successfully | Found as per expectation |  |  | Passed
73 |  |  |  | Verify that the useer can unselect a selected checkbox | unselect a selected checkbox | The check box should be unchecked | Found as per expectation |  |  | Passed
74 |  |  |  | Verify that products are filtered when a feature is selected | filtered when a feature is selected | Only products with 4K feature should be filtered | Found as per expectation |  |  | Passed
75 |  |  |  | Verify that multiple features can be selected together | multiple features can be selected together | User can selected multiple option | Found as per expectation |  |  | Passed
76 |  |  |  | Verify that the express delivery option is working properly | express delivery option | The system shuld express delivery system | Not found as per expectation |  |  | Failed
77 |  |  |  | Verify that hte products are displayed under the free delivery option | The products are displayed under the free delivery option | The system should be displayed properly | Not found as per expectation |  |  | Failed
78 |  |  |  | Verify that the free delivery option is selectable | free dellivery option is selectable | The freed delivery option color should change | Found as per expectation |  |  | Passed
79 |  |  |  | Verify that the color changes when clicking on the free delivery option | color changes | The system should be change the color | Found as per expectation |  |  | Passed
80 |  |  |  | Verify that the free delivery details is working or not | free dellvery details link work or not | The system should be work properly | Found as per expectation |  |  | Passed
81 |  |  |  | Verify that products are displayed based on the selected processor size | based on the selected processor size | The system should be selected based on the processor size | Found as per expectation |  |  | Passed
82 |  |  |  | Verify that he ram size option is clickble | RAM size is clickable | The system should be clickable and displayed | Found as per expectation |  |  | Passed
83 |  |  |  | Verify that the all size availble in displayed message | All size available properly show | The system should be show all size | Found as per expectation |  |  | Passed
84 |  |  |  | Veirfy that the clickable all size | Clickale all size | The system should be clickable and displayed | Found as per expectation |  |  | Passed
85 |  |  |  | Verify that the ram option is working properly | processor option is working | The system should be wrok properly | Found as per expectation |  |  | Passed
86 |  |  |  | Verify that the ram size is displayed correctly | processor rsize | The system should be wrok properly and displayed | Found as per expectation |  |  | Passed
87 |  |  | Footer Section | Verify the footer is displayed on the Home page | Display on Home page | should display on Home page | Found as per expectation |  |  | Passed
88 |  |  |  | Verify the Pickaboo logo is displayed in the footer | Pickaboo logo display in footer | should display in footer | Found as per expectation |  |  | Passed
89 |  |  |  | Verify the "About Us" link is clickable | click in "About Us" | Should clickable | Found as per expectation |  |  | Passed
90 |  |  |  | Verify the "Cookie Policy" link is working | Click in "Contact Us" | Should clickable | Found as per expectation |  |  | Passed
91 |  |  |  | Verify the Privacy Policy link | Click on privacy policy link | should cllickable | Found as per expectation |  |  | Passed
92 |  |  |  | Verify the Terms & Conditions link | see the terms and conditions llink | should display appropriately | Found as per expectation |  |  | Passed
93 |  |  |  | Verify the Return Policy link | cllick return pollicy link | should clickable properly | Found as per expectation |  |  | Passed
94 |  |  |  | Verify the FAQ link | click on FAQ link | should clickable properly | Found as per expectation |  |  | Passed
95 |  |  |  | Verify the Careers link | click on careers link | should cllickable and display properly | Found as per expectation |  |  | Passed
96 |  |  |  | Verify the Facebook icon redirects correctly | click on facebook icon | should go on the facebook pa | Found as per expectation |  |  | Passed
97 |  |  |  | Verify the YouTube icon redirects correctly | click on YouTube icon | should go on the YouTube page | Found as per expectation |  |  | Passed
98 |  |  |  | Verify the Instagram icon redirects correctly | click on Instagram icon | should go on the Instagram icon | Found as per expectation |  |  | Passed
99 |  |  |  | Verify copyright information is displayed | see the copyright information | cpyright information section should exist | Found as per expectation |  |  | Passed
100 |  |  |  | Verify footer layout on different screen sizes | footer layout in screen size | footer layout should on different scrreen size | Found as per expectation |  |  | Passed
101 |  |  |  | Verify all footer links are valid | see if all the links are valid | fall footer links should be vaild | Found as per expectation |  |  | Passed
102 |  |  |  | Verify that all required social media links are presenr in the footer | required social media | must be linked all social media | Found as per expectation |  |  | Passed
103 |  |  |  | Verify that the email in the footer is linked correctly | email in the footer is linked correctly | clicking the email should open the default email | Not found as per expectation |  |  | Failed
104 |  |  |  | Verify that the email is displayed in the footer section | email is displayed in the footer section | its mendatory for the user | Found as per expectation |  |  | Passed
105 |  |  |  | Verify that the telephone number is displayed in the footer section | telephone number in footer section | it s mendatory for the user | Found as per expectation |  |  | Passed
106 |  |  |  | Verify that the address in the footer is linked to google map | address is linked in google map | must be linked to google maps | found as per expectation |  |  | Passed
107 |  |  |  | Verify that the address is dislayed in the footer section | address in footer section | the address system must be available | Found as per expectation |  |  | Passed
108 |  |  |  | Verify that the footer section cintains all required elements | all required elements | all requirement elements are available | Found as per expectation |  |  | Passed
109 |  |  |  | Veirfy that the about section content is correct and complete | about section | all content should be present and correct | Found as per expectation |  |  | Passed
110 |  |  |  | Verify that the help section content is available or not | help section | all content should be present and correct | Found as per expectation |  |  | Passed
111 |  |  |  | Verify that the play store download link is present | playstore link | its mendatory for the user | Found as per expectation |  |  | Passed
112 |  |  |  | Verify that the apps store download link is present | appstore link | Its mendatory for the user | Found as per expectation |  |  | Passed
113 |  |  |  | Verify that the app gallery download link is present | App Gallery Link | Its mendatory for the user | Found as per expectation |  |  | Passed

## Test Summary Report
Test Case Report
Project Name | Pickaboo.com
Module Name | Full Website
Feature Name | All
Test Case Version | 1
Written By | Jannatul Ferdous Samia
Executed By | Jannatul Ferdous Samia | [5 empty] | Result :
Reviewed By | xx
TEST EXECUTION REPORT | [5 empty] | Total No. | Status
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC | 102 | PASS
| 102 | 11 | 0 | 0 | 113 | 11 | FAIL
Grand Total | 102 | 11 | 0 | 0 | 113 | 0 | Not Executed | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
[6 empty] | 0 | Out of Scope
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
# SL 01 Verify that the type of minimum character in search box
Issue: Registered with invalid email address.
Reproducing Steps:
1. Goto the URL https:/www.pickaboocom.bd 2. Click on search box
Env: Productizn.
Module: Register
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: Search minimum character in search box
Expected: The system should display an error message if the user enters fewer characters than the minimum required
Responsible QA: Jannatul Ferdous Samia
Bug Reporting
# SL 02
Issue: Click on "Forgotten Password?" and Account deleted
Reproducing Steps:
1. Goto the URL https://www.startech.com.bd 2. Click on the Login button at the right corner 3. Fill all the fields with invalid credentials 4. Click ''Forgotten Password?"
Env: Production
Module: Login
Severity: P2
Screenshot: "Forgotten Password" error
Responsible QA: Tashfiquzzaman
Bug Reporting
# SL 03
Issue: First and last names should not start with a special character.
Reproducing Steps:
1. Goto the URL https:/www.startech.com.bd 2. Click on the Register button at the right corner. 3. Fill all the fiels with valid credentials
4. Click 'Continue'.
Env: Production.
Module: Register
Severity: P4
Screenshot: First and last names should not start with a special characte
Responsible QA: Tashfiquzzman
Bug Reporting
# SL 04
issue:First name and last name should not start with number.
Reproducing Steps:
1. Goto the URL https://www.startech.com.bd 2. Click on the Login button at the right corner 3. Fill all the fields with invalid credentials 4. Click ''Forgotten Password?"
Env: Production
Module: Login
Severity: P5
Screenshot: First name error
Responsible QA: Tashfiquzzaman
Bug Reporting
# SL 05
issue: A comma should not be expected between the name field.
Reproducing Steps:
1. Goto the URL https://www.startech.com.bd 2. Click on the Login button at the right corner 3. Fill all the fields with invalid credentials 4. Click ''Forgotten Password?"
Env: Production
Module: Login
Severity: P6
Screenshot: Comma error in first name.
Responsible QA: Tashfiquzzaman

## Test Metrics
Test Metrics
Test Metrics
| #SL | Metrics | Description | Result (%)
| 1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (50/50)*100 = 100
| 2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/50)*100 = 0
| 3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (45/50)*100 = 90%
| 4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (5/50)*100 = 10%
| 5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/50)*100 = 0
| 6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
| 7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
| 8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
| 9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
| 10 | Defect Age | Fixed date - Reported date | N/A
| 11 | Customer Satisfaction | No. of complaints per Period of Time | N/A